

**COS30045 Data visualisation**

**Assignment 3A – Project standup 2 submission point**



**Date: Thursday, 12 September 2024**

**Team 01B**

**Thang Truong -** [**103422254@student.swin.edu.au**](mailto:103422254@student.swin.edu.au)

**Linh Doan - 104924340**[**@student.swin.edu.au**](mailto:105465125@student.swin.edu.au)

**Mentor: May Peng Yeo**

**Email: myeo@swin.edu.au**

Table of Contents

[A. Project standups 2 1](#_Toc177075788)

[ List of what we have been done since the project standup 1 1](#_Toc177075789)

[ Estimate of our contribution (in hours and percentage of work completed by the team so far) to 2](#_Toc177075790)

[ Summary of tasks to be completed before the next meeting 2](#_Toc177075791)

[ Issues with teamwork 2](#_Toc177075792)

[B. Oral Report 2](#_Toc177075793)

[ What have you done on the project since it commenced/the last standup? 2](#_Toc177075794)

[ What do you plan to complete before the next standup? 3](#_Toc177075795)

[ What obstacles are you facing in completing your deliverables 3](#_Toc177075796)

[ Short written report of achievement so far and plan for the future. 4](#_Toc177075797)

[C. Draft Version of the work completed so far including 5](#_Toc177075798)

[- Dataset: 5](#_Toc177075799)

[- Version of report: 5](#_Toc177075800)

[- Version of code: 5](#_Toc177075801)

# Project standups 2

## List of what we have been done since the project standup 1

* Recognize and validate the attributes and interpret the storytelling elements from the two datasets.
* Working on the assignment 3B-Project Process Book.
* Review practical labs.

## Estimate of our contribution (in hours and percentage of work completed by the team so far) to

* Finding and working with dataset:
  + Four working days and 8hrs per day as 40 percentage completed.
* Designing the visualisation
  + Four working days and 8hrs per day as 40 percentage completed.
* Contributing to writing up Assignment 3B-Project process book
  + Four working days and 8hrs per day as 40 percentage completed.
* Writing/researching code
  + Four working days and 8hrs per day as 40 percentage completed.

## Summary of tasks to be completed before the next meeting

* Completed Assignment 3A-Project standups 2 and should be submitted by 22nd-September-2024.
* Acknowledge 2 datasets from OCED Health Statistic website and continue to contribute workload to the Assignment 3B-Project Process Book and Assignment 3C-Website and Visualisation.

## Issues with teamwork

* We are working well and have no issues.

# Oral Report

## What have you done on the project since it commenced/the last standup?

Team member: - 103422254 (Thang Truong)

* Verify attributes and focusing on the impact of storytelling from two datasets.
* Contribute to the workload for assignment 3B-Project process book.
* Collaborate with team members on project’s requirements using Slack.

Team member: - 104924340 (Linh Doan)

* Coming soon . . .

## What do you plan to complete before the next standup?

Team member: - 103422254 (Thang Truong)

* Assignment 3B-Project process book should be completed more than sixty percent of total workload.
* Acknowledge and understand the role of storytelling from two datasets.
* All practical labs should be done.

Team member: - 104924340 (Linh Doan)

* Coming soon. . .

## What obstacles are you facing in completing your deliverables

Team member: - 103422254 (Thang Truong)

* I have no issues so far. Thanks to my classmates and eLA who have cleared up my doubts from discussion board on Canvas.
* Teammates are collaborating well.

Team member: - 104924340 (Linh Doan)

* Coming soon. . .

## Short written report of achievement so far and plan for the future.

Team member: - 103422254 (Thang Truong)

After submitting Project Standup 1, we achieved several milestones, including acknowledging two datasets. Our team members are currently working on Assignment 3B - the Project Process Book, focusing on understanding the role of storytelling from datasets. Additionally, we are reviewing all practical labs to contribute to Assignment 3C - Website and Visualization

For the next standup, I plan to increase productivity by dedicating 24 hours (3 working days at 8 hours per day) to working on Assignment 3B, which is currently 40% complete.

Designing the visualization is crucial for readability and attractiveness. Therefore, I will allocate 24 hours (3 working days at 8 hours per day) to this task, focusing on understanding the role of storytelling from two datasets and creating the user interface for Assignment 3C - Website and Visualization, which is currently 40% complete.

Writing and researching code is the most crucial part of the project. I plan to spend 24 hours (3 working days at 8 hours per day) reviewing all practical labs, which are currently 40% complete.

Finally, I would like to summarize the to-do items before our next standup. We need to acknowledge two datasets and understand the role of storytelling, focusing on contributing to Assignment 3B - Project Process Book. There are no issues with the practical labs.

Team member: - 104924340 (Linh Doan)

* Coming soon. . .

# Draft Version of the work completed so far including

## Dataset:

* + Version 1.0
  + Credit: https://github.com/thangtruong1808/COS30045-Data-Visualisation/tree/main/Assignment%203C-Website%20and%20visualisation/Coding/datasets

## Version of report:

* + Version 1.1
  + Credit: https://github.com/thangtruong1808/COS30045-Data-Visualisation/tree/main/Assignment%203B-Project%20process%20book

## Version of code:

* + Version 1.1 using D3 library version 6.
  + Credit: https://github.com/thangtruong1808/COS30045-Data-Visualisation/tree/main/Assignment%203C-Website%20and%20visualisation/Coding